## Sheet1
Stage	Analysis, docs, design	Front End	Back End	Mobile	CI/CD
1.Proto MVP	1. High level plan	1. Create base project structure (SPA)	1. Create base project structure	1. Create base project structure (SPA)	1. Run apps in dev mod (script)
	2. Manage issues	2. Define tech stack	2. Define tech stack	2. Define tech stack	2. Start project docs
	3. Readme.md	3. Proto auth page	3. Proto auth	3. Proto auth page
	4. Description of main entities	4. Proto home page (without border)	4. Endpoint with proto statistics for home page	4. Proto home page (without border)
	5. Repo structure creation	5. Border		5. Border
	6. Proto design (home page, border, user account, project, find user, find project)	6. Proto user account page	5. CRUD user endpoint	6. Proto user account page
		7. Proto project page	6. CRUD project endpoint	7. Proto project page
		8. Proto find user page	7. Extend user endpoit with find/filter method	8. Proto find user page
		9. Proto find project page	8. Extend project endpoit with find/filter method	9. Proto find project page

2.MVP	1. Manage issues	1. Instruments adjusting	1. Instruments adjusting	1. Instruments adjusting	1. Run apps in dev mod (task)
	2. Tests strategy (functional requirements)	2. Auth page	2. Security check	2. Auth page	2. Build (task)
	3. Multilanguages	3. Add admin layer	3. Add admin layer	3. Add admin layer	3. Deploy (task)
		4. Home page (without border)		4. Home page (without border)	4. Run build (task)
		5. Border		5. Border	5. Test (task)
		6. User account page		6. User account page
		7. Project page		7. Project page
		8. Find user page		8. Find user page
		9. Find project page		9. Find project page
		10. Add tests ?	4. Add tests ?	10. Add tests ?
		11. Multilanguages	5. Mutilanguages	11. Multilanguages
	4. Thematization ?	12. Thematization ?	6. Thematization ?	12. Thematization ?

3. MVP Prod	1. Manage issues	1. Add monetization instruments? (ads?)	1. Add monetization instruments? (ads?)	1. Add monetization instruments? (ads?)
	2. Improve Readme.md	2. Add stability instruments?	2. Add stability instruments? (check stability strategy? DB backup, server reloading...)	2. Add stability instruments?
	3. Think about monetization strategy (do we need it?)	3. Add metrics?	3. Scaling ???	3. Add metrics?
	4. Domen name	4. SEO?		4. Deploy strategy ?
	5. Hosting vs cloud	5. SSR migration?
	6. Introducing on youtube, habr, linkedin
	7. Finance strategy (foresee support costs)
	8. Marketing strategy
	9. Define strategy of search for users according to project	6. Find users by project	4. Find users by project	6. Find users by project
	10. Define strategy of search for projects according to user	7. Find projects by user	5. Find projects by user	7. Find projects by user
	11. Chat?	8. Chat?	6. Chat?	8. Chat?

Backlog	- CV uploading
	- video intro for project uploading
	- improve user profile (add image etc.)
	- chats filtrarion by project, by skills
	- favorits project
	- friends
	- hide user profile
	- hide user skill
	- skill group
	- about me file generation (and about me history)
	- hide about me history